## Small Works Contract
SMALL WORKS CONTRACT TEMPLATE
This contract is drawn up between..
Organisation: |  | Contractor:
Represented by: |  | Represented by:
Description of the works, goods or services to be undertaken..
CONSTRUCTION OF [XYZ] EMERGENCY TAPSTANDS (WOODEN PALLETS) AS PER UNHCR TECHNICAL SPECIFICATION AND TECHNICAL DRAWINGS (REF: D300-2015A)
Timetable of activities..
THE CONTRACTOR SHOULD AIM TO FINISH THE WORKS DESCRIBED WITHIN [XYZ] WEEKS OF SIGNATURE OF CONTRACT.
Terms of payment..
THE ORGANISATION WILL PAY A TOTAL CONTRACT PRICE OF [XYZ] USD$ ACCORDING TO THE FOLLOWING TERMS AND CONDITIONS..
20% ADVANCE
50% UPON COMPLETION OF 50% OF THE WORKS
30% UPON COMPLETION AND FINAL INSPECTION
Conditions and penalties..
1. | THE CONTRACTOR MUST WORK IN CLOSE COLLABORATION WITH THE WASH AGENCY SITE ENGINEER.
2. | THE WASH AGENCY WILL PROVIDE THE TAPSTAND KIT AND HDPE PIPE UP TO THE TAPSTAND LOCATIONS.
3. | THE CONTRACTOR IS RESPONSIBLE FOR PROVIDING ALL OTHER MATERIALS, TRANSPORT AND LABOUR TO COMPLETE THE CONTRACT.
4. | THE CONTRACTOR MUST CORRECT ALL LEAKS OR DEFECTIVE WORK THAT DOES NOT MEET THE SPECIFICATIONS OR TECHNICAL DRAWINGS BEFORE FINAL PAYMENT IS MADE.
5. | THE ORGANISATION RESERVES THE RIGHT TO CANCEL THE CONTRACT AT ANY TIME. PAYMENT WILL BE PROPORTIONAL TO WORK COMPLETED.
I agree to the content of this contract..
For the organisation: |  | For the contractor:
Name: |  | Name:
Signature: |  | Signature:
Date: |  | Date:
Witnesses..
Name: |  | Name:
Signature: |  | Signature:

## Bill of Quantities
BILL OF QUANTITIES
CONSTRUCTION OF [XYZ] EMERGENCY TAPSTANDS (WOODEN PALLETS - REF: D300-2015A)
NO | ITEM | UNIT | QTY | RATE | AMOUNT
PRELIMINARIES
1.1 | Mobilization of equipment, labour and materials. | pc | 1
SITE WORKS
2.1 | Clearing and levelling of site 6m x 3m. | m2 | 18
2.2 | Excavation of soil up to 25cm deep including removal of surplus off-site as directed. | m3 | 0.84
2.3 | Soil percolation test as per Appendix 20 of Engineering in Emergencies. | pc | 1
2.4 | Excavation of soakage pit up to 1m deep including removal of surplus soil off-site as directed. | m3 | 3.14
2.5 | Supply and installation of 20cm deep gravel bed perfectly levelled as per specification and technical drawings. | m3 | 0.67
2.6 | Supply and installation of 80cm deep gravel bed perfectly levelled as per specification and technical drawings. | m3 | 2.5
2.7 | Covering of drainage trench and soak pit with plastic sheeting as per specification and technical drawings. | m2 | 3.62
2.8 | Covering of drainage trench and soak pit with 10cm compacted soil as per specification and technical drawings. | m2 | 3.62
2.9 | Supply and installation of 3 wooden euro pallets installed perfectly level as per specification and technical drawings. | pc | 3
PLUMBING WORKS
3.1 | Assembly and installation of tapstand (six taps) as per assembly instructions. Tapstand to be installed straight and level with taps 50cm above wooden pallet surface. Tapstand to be pressure tested by WASH Agency to 10 atm and all leaks corrected. WASH Agency to provide tapstand kit, 32mm HDPE pipe and PTFE tape. | pc | 1
TOTAL AMOUNT FOR CONSTRUCTION OF ONE TAPSTAND
TOTAL AMOUNT FOR CONSTRUCTION OF [XYZ] TAPSTANDS