## Slide 1: CAMP CLOSURE
Module 9
Notes: <number>

## Slide 2: Learning Objectives
Define camp closure and describe the types involved
Understand the link between camp closure and durable solutions for refugee populations
Understand the primary opportunities and challenges of achieving durable solutions for refugees
Appreciate the importance of closing camps properly, whether it is an abrupt or planned closure
Describe the camp closure process and its components: situation analysis, planning, roles and responsibilities of key actors, coordination mechanisms & information management at the national and camp level
Understand the main elements of a closure action plan
Notes: <number>

## Slide 3: Three Phases of a Camp
Planning
& set-up
Care,
maintenance
& management
Phase out &
Closure
Notes: <number>
Explain that the Camp Management training modules attempt to cover the three phases of a camp’s life. Those phases may very often overlap but provide a good framework within which to consider management of the camp. The life of a camp is dynamic and the needs of the camp community change over time. It is the task of the Camp Management Agency to work flexibly and to plan and coordinate with a range of actors involved in each phase, from the time it is set up to the identification of durable solutions, phase-out and camp closure. Often the Care, Maintenance & Management phase of a camp’s life can last much longer than anticipated. Ensuring the day to day upkeep of the camp, the participation of camp residents, repairs, developments and the provision of assistance and services is central to the work of a Camp Management Agency.

## Slide 4: What is Camp Closure?
Similar to camp set-up, camp closure is a
context- specific process. It can take place
for a variety of reasons, and in different
ways or stages – from planned and orderly
closure influenced by organized return
movements, to abrupt
and chaotic closure.
(Camp Management Toolkit, Chapter 7).
©UNHCR/S.Halili
Notes: <number>

## Slide 5: Abrupt Camp Closure
    Spontaneous abrupt: Unforeseen circumstances lead refugees
    to leave the camp suddenly on their own
    Planned abrupt: A sudden change of situation is known and the
    humanitarian community and government may assist with closure,
    to the extent possible
    Forced abrupt: A situation in
    which the population is driven
    out of the camp by force, e.g.
    by warring parties, government
    coercion or land owners
©MONUC/Marie Frechon

## Slide 6: Planned Camp Closure
A process that takes place in an orderly fashion in
which proper preparation, planning and
implementation of phase out and closure are carried
out within a thoughtful exit strategy, ideally leading to
a durable solution for refugees.
Planned closure generally happen in three ways:
Durable Solutions
Consolidation
Re-location

## Slide 7: Planning Camp Closure
Notes: <number>

## Slide 8: Durable Solutions
The implementation of durable solutions for displaced populations is the driving force behind the camp closure process.
– Camp Management Toolkit, Chapter 7
Notes: <number>

## Slide 9: Durable Solutions for Refugees
Voluntary repatriation to the country of origin
Local integration in the country of asylum
Resettlement to a third country
Notes: As a general principle, the best solution is voluntary repatriation. Where this is not possible, assimilation within the country of asylum (local settlement) is in most circumstances preferable to assimilation within another country (resettlement). This is particularly true for large groups and in cases where resettlement would take place in a cultural environment alien to the refugees. There may, however, be situations in which resettlement is the only way to ensure protection.
SOURCE: UNHCR Handbook for Emergencies , Chapter on Voluntary Repatriation
<number>

## Slide 10: Principles to Guide Durable Solutions
The decision whether or not to return home belongs to the refugees
Repatriation should be based on a free and informed decision and take place in safety and dignity
The voluntary nature of the repatriation must be verified and safeguarded by UNHCR and its partners
International protection for those who choose to stay longer in the country of asylum must be ensured
If refugees who remain are unlikely to return home, local integration and resettlement may need to be considered as durable solutions
Notes: Principles of response – additional information
Voluntary Repatriation
Refugees should neither be forced to return, nor prevented from doing so. The decision is made freely.
The refugees are making an informed decision based on an accurate country profile.
Voluntary return should only be undertaken where there has been a fundamental change in the circumstances causing displacement.
Its success largely depends upon the achievement of a reintegration process relentlessly supported by all stakeholders.
Continued asylum for those who remain refugees
Some refugees may continue to harbor a well-founded fear of persecution and therefore would not wish to repatriate.
Others may delay their decision, or decide against repatriation, preferring to wait and see until more persons have returned successfully.
This may mean the continuation of any existing operation, but for a reduced number of beneficiaries. Any voluntary repatriation operation will have to be planned and conducted in the context of a broader comprehensive strategy for durable solutions. If refugees remaining in the country of asylum are unlikely to be willing to return home, based on their particular profile and their specific needs, local integration and resettlement may need to be considered as durable solutions
If there is a serious problem of coercion, or intimidation, it may be necessary to move those who decide not to repatriate to another location immediately after they have reached this decision. This, too, should be foreseen and covered in any voluntary repatriation agreement.
Source: UNHCR Handbook for Emergencies

## Slide 11: Preparing for the Camp Closure Process
To begin, we need to analyze the context in order to understand the reality on the ground
This is done through a situational analysis: it is critical for effective planning
The analysis happens at two levels: national and local/camp level
All stakeholders need to participate and be involved
Notes: <number>

## Slide 12: Brainstorm
What kind of information is needed to conduct a situational analysis?
Notes: <number>

## Slide 13: Situational Analysis
National Level
Situational Analysis
  Scenarios
  Political
  Economic
  Social
  Resources
  Timing
  Population figures
Camp Level
Situational Analysis
  Population figures
  Refugees’ intentions
  Timing
  Protection
  Compensation
  Land
  Logistics
  Security
  Environment
  Infrastructure
Processes
Strategy and Plans
Exit Strategy
Based on national level analysis
Informs the action plan
Camp Closure Action Plan
Mirrors the Exit strategy
Based on the situation analysis at the camp level
Notes: At the National Level, information to be included in the situational analysis include: security considerations and information relating to Durable Solutions
At the Camp Level, information to be included in the situational analysis include: camp map/layout, list of what agencies are involved in what sectoral activities, an analysis of the host community
<number>

## Slide 14: Exit Strategy (National Level)
The EXIT STRATEGY is a contingency plan that addresses various camp closure and durable solution scenarios. It also provides an overall contextual premise for which national and local authorities and humanitarian actors achieve camp closure
The purpose is to facilitate a smooth transition from emergency to early recovery in order to assist the returning community to rebuild their lives
The Exit Strategy informs the camp level Action Plan
Notes: <number>

## Slide 15: Action Plan (Camp Level)
The ACTION PLAN elaborates concrete objectives and deliverables, sectoral considerations, tasks and responsibilities, required resources and appropriate timelines
The purpose is to provide a concise, holistic plan for phasing out humanitarian assistance and detail the camp closure process
Both the exit strategy and action plan need to consider the needs of people as well as infrastructure
Notes: <number>

## Slide 16: Camp Closure Process
Information Management
National Level
Camp Level
Situational Analysis
Exit Strategy
Policy and framework for local planning
Coordination Mechanism:
HC/RC; National Govt; UNHCR; Humanitarian and Development Actors
National level Agreements
MOUs, Legal commitments
Coordination Mechanism:
Camp Management & Coordination actors; National & Local Govt; Humanitarian and Development Actors; Refugees
Regional/Local Action Plan
Components of national strategy
Implementation plan
Division of activities and partners
People
Refugees
Feedback mechanism to
the National level
Residual
Populations
Host
Population
Sectors
Handover assets and facilities
Infrastructure and environmental rehabilitation
Infrastructure
& Environment
Information Management
Notes: <number>

## Slide 17: What is Important for the Process?
Planning: Exit Strategy & Action Plan
Supporting legal documents: e.g., National MOU with Government, local agreements with other partners
Coordination among key stakeholders: establish Camp Closing Committee, usually chaired by UNHCR
Information Management: data collection, information sharing and dissemination
Participatory & Inclusive Approaches
Notes: Some other factors that may be raised or mentioned include: resources, capacity, Information Management system in place and understood by all parties
<number>

## Slide 18: Developing a Closure Action Plan
What are Components of the Action Plan?
Defined objectives
Deliverables
Roles & responsibilities
Required resources
Timelines
Sector considerations
Notes: <number>

## Slide 19: Who are the Key Stakeholders?
UNHCR
Camp management agency
Refugees
Host Government
Humanitarian & Development Actors
Government of Country of return
Host Community
Notes: In a refugee context, UNHCR plays a lead role
UNHCR, the camp management agency, refugees, host government, humanitarian/development actors and host community. When repatriation is part of the camp closure, the government in the country of return is also involved, generally through a tripartite agreement
<number>

## Slide 20: Action Plan Considerations
Looking at the Needs of People:
Protection issues, security, monitoring mechanisms and refugees’ intentions
Information Management Strategy: Is data complete? Up to date? Accessible to all?
Legal considerations: Is documentation available (immunizations, birth certificates)?
De-registration and Return & Reintegration
Sector Considerations: Health, Early Recovery, Shelter, Education etc.
Looking at Infrastructure & Environmental Needs:
Inventory of Assets and Infrastructure
Decommissioning: Rehabilitation plans, Handover of assets & responsibility for services
Environmental considerations: Waste disposal, Fill latrine pits, Reforestation
Compensation policies for clean up
Notes: <number>

## Slide 21: The Scenario (Future Closure)
Even if you are currently not involved in a process for camp closure in your country, this is the ultimate aim of any settlement.
Imagine that one of the camps or collective centres you work in is approaching a planned closure. Durable solutions have been identified for its population. You have a month to plan and ensure that the closure is successful. What are the key steps and elements you would need in an action plan for closure?
Notes: THIS IS FOR a country that does not have an actual camp closure on the horizon
<number>

## Slide 22: The Scenario (Imminent Closure)
The camp in your country context is closing. Although there may not be much time, it is still important to plan for a responsible closure, as best we can.
What are the key steps and elements you need in the camp closure action plan?
Notes: THIS IS FOR a country that is working with an actual, imminent closure.
<number>

## Slide 23: Group Work Develop an Action Plan for Closure
People or Infrastructure Need? | Specific Activity or Action | Who is Responsible?
Notes: <number>

## Slide 24: Review Camp Closure
The implementation of durable solutions for displaced populations is the main driving force behind a camp closure process. Closure can also result from other reasons such as relocation of camp residents to another location or site.
Return must be voluntary. Refugees must be provided with information and support in order to make an informed and voluntary choice about their preferred durable solution, and also participate in the planning and management of that choice.
The starting point for any strategy, plan or process must take into consideration the operating environment or what is called the situational analysis.
The camp closure process requires consultation, coordination and planning at both the national and camp level. The exit strategy and action plan for closure are concrete outputs on the two levels.
Roles and responsibilities relating to camp closure must be well defined to ensure common understanding, clear expectations and effective management and coordination of the process.
KEY MESSAGES
Notes: <number>