# Camp Closure

# 90 or 120 minutes (Optional Module)

## Why does this session matter?

This module outlines what camp closure is, highlights why it is important, and establishes its critical link with Durable Solutions. It details the components of the camp closure process, including roles and responsibilities, situational analysis, planning, coordination, and information management among all actors, both at the national level and the local level. The action plan for closing camps draws on an exit strategy (ideally developed at the national level with the involvement of all relevant stakeholders). The plan focuses on addressing the needs and concerns of people on the one hand and infrastructure requirements on the other.

## Learning Objectives

- At the end of this session participants will be able to:

- Define camp closure and name the types involved.

- Understand the link between camp closure and durable solutions for refugee populations.

- Understand the primary opportunities and challenges presented by achieving durable solutions for refugees.

- Appreciate the importance of closing camps properly, whether it is an abrupt or planned closure.

- Describe the camp closure process and its components: situation analysis, planning, roles and responsibilities of key actors, coordination mechanisms & information management at the national and camp level.

- Understand the main elements of a camp closure action plan.

## Key Messages

- The implementation of durable solutions for displaced populations is the main driving force behind a camp closure process. Closure can also result from other reasons such as relocation of camp residents to another location or site.

- Return must be voluntary.  Refugees must be provided with information and support in order to make an informed and voluntary choice about their preferred durable solution, and also participate in the planning and management of that choice.

- The starting point for any strategy, plan or process must take into consideration the operating environment or what is called the situational analysis.

- The camp closure process requires consultation, coordination and planning at both the national and camp level. The exit strategy and action plan for closure are concrete outputs on the two levels.

- Roles and responsibilities relating to camp closure must be well defined to ensure common understanding, clear expectations and effective management and coordination of the process.

## Session Plan

| Activity |  | Topic | Method | Timing |
| --- | --- | --- | --- | --- |
| 1 |  | Camp Closure Defined & Types | Presentation | 10’ |
| 2 |  | Durable Solutions | Presentation with Q&A | 10’ |
| 3 |  | The Camp Closure Process | Presentation with Brainstorming Exercise | 18’ |
| 4 | A | Developing a Camp Closure Action Plan | Group Work & Plenary Debrief | 50’ |
|  | B | Developing a Camp Closure Action Plan (extended version) | Group Work & Plenary Debrief | 80’ |
| 5 |  | Review of Camp Closure | Presentation | 2’ |

## Handouts

- Framework for Durable Solutions, for refugees and Persons of Concern (optional)

- Situational Analysis Chart

- Camp Closure Process Chart Flowchart

- For Activity 4A/B: Camp Closure: Issues to Consider with Guiding Questions & Notes

- For Activity 4A/B Debrief: Table for Camp Closure Action Plan

## Key Resource Documents

- Framework for Durable Solutions for refugees and Persons of Concern, UNHCR Geneva, May 2003

- UNHCR Handbook on Voluntary Repatriation: International Protection 1996

- Camp Management Toolkit, Chapter 7

- UNHCR Handbook for Emergencies 3rd edition,  Chapter 22

## Supplies Needed

- Flip chart paper & pens

- Blu-tac

- Laptop, projector and screen

## Planning

- Review and set up PowerPoint

- Prepare flipcharts for Activity 4A/B

- Prepare blank ‘Action Plan templates’ on Flipchart Paper (3 pages per each group in Activity 4)

- Trainer needs to be familiar with Resource documents

## Trainer Notes on Running Module 8

This module gives participants an understanding of the approach and overall process of camp closure and developing an action plan.  This module contains a lot of information so the Trainer needs to move the session along to cover all the material in a timely manner. This must be balanced against assuring the information is conveyed concisely and that participants understand the material and are able to effectively apply it in the final exercise: developing an action plan. This exercise is available in a condensed (4A) and extended (4B) format. The trainer needs to select the appropriate version, based on the time available and the importance of the subject matter for the local context.  The trainer also needs to revise the PowerPoint, by choosing the correct scenario – imminent or future camp closure – and modify the description if necessary to reflect the actual situation.

## Activity 1 – Camp Closure Defined & Types – 10‘

Show slide:  Learning Objectives

- Briefly review the learning objectives of the module.

Show slide:  Three Phases of a Camp

- Remind: Camps are established for the welfare and protection of refugees. They are created with the intention of being a temporary structure. Refer to material covered in Care & Maintenance and the Standards Modules, if your group participated in these optional modules.

- Explain: Camp closure is an integral and inevitable part of the camp life-cycle.

- State: The term ‘camps’ will be used throughout the module for simplicity, but is intended to represent both camps and collective centers.

Show slide: What is Camp Closure?

- Present the title of the slide only.

- Ask: What do participants associate with ‘camp closure’? Solicit a few responses, and then reveal definition (click).

- State: These different scenarios can be divided into two broad categories: Abrupt & Planned.

Show slide: Abrupt Camp Closure

- Present the title of the slide only.

- Explain: Abrupt closures occur due to a sudden change in the context of an existing camp.

- State: There are three types of abrupt closure & describe each one as you reveal text (click).

- Spontaneous abrupt: when refugees leaves suddenly on their own, for example, due to a natural disaster, insecurity, insufficient or lack of provisions or services, without support from the humanitarian community.

- Planned abrupt: where the sudden change of situation is known and the humanitarian community and governments may assist with the closure and movement of the refugees but without the time to allow for proper preparation, planning and implementation.

- Forced abrupt: when the population is dispersed and driven out of the camp, e.g. by warring parties, government coercion or land owner eviction.

- Emphasize the heightened protection risks for refugees in all abrupt camp closures.

Show slide: Planned Camp Closure

- State: A process that takes place in an orderly fashion in which proper preparation, planning and implementation of phase-out and closure are carried out within a proper exit strategy, ideally leading to a durable solution for refugees.

- Add a cautionary note: This definition describes the ‘ideal’ way that a camp is closed, and this module will present prescriptive process, while the plenary and group work exercises will provide opportunities to discuss real life scenarios.

- Describe: Planned closures generally happen in three ways:

- Durable Solutions: refugees are able to freely choose to return, integrate or re-settle voluntarily in safety and with dignity.

- Consolidation: remaining population of more than one camp is moved to a single camp or from one side or scattered around is moved to one location of the same camp necessitating decommissioning of the vacated areas.

- Relocation: transfer of refugees to another site or other temporary location.

## Activity 2 – Durable Solutions – 7‘

Show slide: Planning Camp Closure - Photo

- State: Whatever the specific circumstances that prompt the closure of a camp, we have a duty to close the camp as responsibly as possible within the specific context.

- Explain: This is most feasible in a situation where the process is planned, and therefore, ‘planned closures’ will be the focus of this training module.

- Remind: Planning for closure starts at the set up phase. Refer to material covered in the Standards & Settlement Design Module, if your group participated in this optional module.

Show Slide: Durable Solutions

Key Message: The implementation of durable solutions for displaced populations is the main driving force behind a camp closure process. Closure can also result from other reasons such as relocation of camp residents to another location or site.

Show Slide: Durable Solutions for Refugees

- Present the title of the slide only.

- Ask: What are refugees’ choices for durable solutions? After soliciting responses reveal the three options (click).

- Explain:  As a general principle, where feasible voluntary repatriation is the most preferred durable solution. Where this is not possible, assimilation within the country of asylum (local settlement) is in most circumstances preferable to assimilation within another country (resettlement).  This is particularly true for large groups and in cases where resettlement would take place in a cultural environment alien to the refugees. There may, however, be situations in which resettlement is the only way to ensure protection. (Source: UNHCR Handbook for Emergencies, chapter on Voluntary Repatriation).

- Explain: It is important to understand that durable solutions are a parallel process that in reality may not always be part of the camp closure/decommissioning process itself. While durable solutions ideally trigger camp closure, these are two different processes. However, actors responsible for camp closure need to be aware of the extent to which the process of durable solutions for refugees is advancing. This information is a decisive factor for planning closure.

Show slide: Principles to Guide Durable Solutions

- Explain: The search for durable solutions is a complex, often lengthy process designed to restore the human rights of refugees. Many actors are involved who need to observe a number of key principles to make the quest for durable solutions a success.

- Review the principles on the slide.  Additional information is available under the slide.

- Explain: These principles are key example excerpted from UNHCR Handbook for Emergencies, Chapter 22 on Voluntary Repatriation.

- Distribute the optional Handout: Framework on Durable Solutions for Refugees, if desired.

Key Message:  Return must be voluntary.  Refugees must be provided with information and support in order to make an informed and voluntary choice about their preferred durable solution, and also participate in the planning and management of that choice.

## Activity 3 – The Camp Closure Process – 20‘

Show Slide: Preparing for the Camp Closure Process

- Review the bullet points on the slide.

- Ask: Why is a situation analysis important?  How might it inform the closure process?  Then move on to a brief exercise.

Show Slide: Brainstorm

- Ask: What kind of information is needed to conduct a situational analysis? Take 2-3 minutes in groups of 3 to discuss. Ask each group to report back on one item, adding only new items rather than reporting duplicates.  Record responses on a flipchart.  Allow no more than 10’ minutes for the entire exercise.

Show slide: Situational Analysis Chart

Key Message: The starting point for any strategy, plan or process must take into consideration the operating environment or what is called the situational analysis.

- Explain: The situational analysis must be undertaken at two levels, national and local/camp level. The national level analysis is the basis of developing an exit strategy, which informs the action plan for camp closure. The situation analysis on camp level reflects macro level factors and most importantly feeds into the camp closure action plan. Highlight the arrows to show how these different components impact each other.

- Review the types of information named on the Situational Analysis Chart and compare it with answers on the flipchart from the brainstorming exercise.

- Ask: How do your responses compare with the chart? Is anything missing?  See notes on bottom of slide for additional types of information that can be collected.

- Apply what is learned by using a context specific example to show how you can draw conclusions for the refugee situation.  The following are two generic illustrations. Replace these with actual examples from the local context.

- Camp level example - Camp population figures: Camp population statistics should exist, disaggregated by age, gender and vulnerability. Population data should also include the nature and number of vulnerable displaced persons. This is essential data to influence decisions on such issues as durable solutions, likely remaining residual population and the possible continuation of services.

- National level example – INSERT A REFUGEE CONTEXT EXAMPLE Political factors:

- Distribute the Handout: Situational Analysis Chart.

Key Message: The camp closure process requires consultation, coordination and planning at both the national and camp level. The exit strategy and action plan for closure are concrete outputs on the two levels.

Show slide: Exit Strategy (National Level)

- Ask a participant to read aloud the definition (first bullet) on the slide.

- Explain: The purpose of the exit strategy is to facilitate a smooth transition from emergency to early recovery in order to assist the returning community to rebuild their lives.

N.B. It would be useful to refer back to the Standards & Camp Design Module if it was held; and the importance of starting to plan for closure from the start at the planning stage; if not covered the need to plan for closure from the beginning should be highlighted here.

- State: The exit strategy informs the camp level action plan.

Show slide: Action Plan (Camp Level)

- Ask another participant to read aloud the definition (first bullet).

- Explain: The purpose of the action plan is to provide a concise, holistic plan and details of the camp closure process including assigning specific roles and responsibilities and timelines.

- Highlight: Often there are multiple plans (e.g. by sector or region); however, for the purposes of this module we are talking about an action plan for one single camp.

- State: Both the exit strategy and action plan need to consider the needs of people and infrastructure.

Show slide: Camp Closure Process Flowchart

- State: The Camp Closure Process flowchart illustrates an ‘ideal’ process that should ensure a smooth and efficient camp phase out and closure.

- Review each of the components highlighting the relationship(s) between them:

- Solid coordination is paramount to the success of this process, on both levels.

- Actors at the National coordination level are responsible for overall guidance and support in the form of an exit strategy. This includes the formulation of any policies and/or legal frameworks/guarantees such as a MOU.

- Local/camp level coordination bodies are responsible for the practical formulation of the camp closure action plan. The coordination process may be undertaken through a consultative body such as a Committee, usually chaired by UNHCR to facilitate the management of camp closure and transition towards durable solutions.

- The camp closure action plan considers people and infrastructure.

- Environmental considerations are of the utmost importance during the closure process.

- A reliable flow of information between the actors on different levels is vital to ensure a smooth and efficient camp closure. The information management is illustrated in the chart as a continuous process.

- Distribute Handout: Camp Closure Process Flowchart.

Show slide: What is Important for the Closure Process?

- Review the slide to briefly recap the key learning points related to the closure process.

## Activity 4A –Developing a Camp Closure Action Plan – 50‘

Show slide: Developing a Closure Action Plan

- Present the title of the slide only.

- Explain: In this exercise, we will be using the actual country context to develop an action plan for camp closure. Remind the participants the aim of all settlements is closure, even if that is not their current situation.

- Reveal the text on the slide (click).

- Explain: Any good action plan needs to have clearly defined objectives, articulated deliverables and clear indications of who is responsible for what. Also, what resources will be required to achieve the objectives and realistic timelines are necessary components of the closure action plan. These need to be applied to all relevant sectors.

Show slide: Who are the Key Stakeholders?

- Present the title of the slide only.

- Explain: To better equip the group to draft an action plan, let’s remember who needs to be involved and also look briefly at issues to consider when developing an action plan.

- Ask: Who needs to be involved in camp closure?

- Take answers in plenary, then reveal list (click).

- Conclude by explaining that not all stakeholders listed participate at both the national and local level.  For example, a Government of the Country of return would participate at the national level when a tripartite agreement is in place.

Key Message: Roles and responsibilities relating to camp closure must be well defined to ensure common understanding, clear expectations and effective management and coordination of the process.

Show slide: Action Plan Considerations

- Present the title of the slide only.

- Ask: What do you think are some key elements in a good closure plan addressing the needs of both people and infrastructure?

- Solicit responses from the group and then reveal (click) sample items on the slide.

- Distribute the Handout: Camp Closure: Issues to Consider with Guiding Questions & Notes.

- Explain: This is a resource tool to use during the group work that further elaborates issues to consider when developing an action plan.

Show Slide: The Scenario (Imminent or Future Closure)

- Read the scenario, using the slide appropriate for the local context.

Guidance from this point forward, is for the ‘short’ version only: 4A

Show Slide: Group Work – Develop an Action Plan for Closure

- Divide the participants into a maximum of 3 groups, to make report back more manageable.  Assure that each group has representation from the different stakeholder groups, if feasible.

- Distribute 3 pre-prepared flip charts to each group: ‘Action Plan Template’ (based on the matrix on the slide; if groups need additional sheets they can make more as needed.)

- State: A Camp Closing Committee, chaired by UNHCR, has been formed.  Your role in this exercise: your small group represents committee members who have been tasked to draft the action plan. Represented in the committee are the relevant stakeholders: the national authority as camp administrator, UNHCR (camp coordination), the agency in charge of camp management (assume for this exercise, it has been delegated to an NGO), refugee and host population representatives, key humanitarian and development organizations.

- Explain: Create an action plan for camp closure, based on your actual country context.  The plan must ensure that refugees are protected and assisted and the vacated site is well-managed.  Use the pre-prepared flip charts as a template for the plan.

- Remind the group that a closure plan considers both people and infrastructure, so for each action/activity, indicate which need it responds to. Also, for each action, identify the responsible actor(s) involved in the closure process. (Reference the “key stakeholder” slide if needed.)

- Explain: Focus on capturing all the ideas your small group generates about what needs to happen to responsibly close the camp. Use the handout to help guide you through issues you need to consider and make them specific to your context. What needs to be emphasized in your plan?

- Allow 20’ for the groups to work on their action plans.

Report Back & Debriefing the Exercise – Allow 15’

The primary objective of the exercise is for participants to identify what needs to be considered, and thus what actions need to be taken by who, when planning a camp closure. Highlight that an actual plan would of course be far more detailed including timelines, resources needed, specific identification of who is responsible at the activity level, etc. For the purposes of this debrief, focus on capturing as many issues that are identified during the report back, and identifying what important considerations were not addressed. Use the Handout: Table for Camp Closure Action Plan to assist as well as the Handout: Issues to Consider with Guiding Questions & Notes.

- Ask each group to post their action plan on the wall for all participants to see.

- Ask each group to present 1-2 items they discussed and included in their action plan, and focus on items not presented by the previous group(s). Strictly adhere to 2’ per group.

- Distribute the Handout: Table for Camp Closure Action Plan. Allow participants to briefly review the handout.

- Facilitate Plenary Discussion:

- Ask: Identify major gaps in your draft action plans compared to the handout.

- Ask: Are there any items on the Table that are not relevant for your context?  Why or why not?

- Ask: Are there other items that need to be considered as part of the action plan?

- State: This was a very rapid exercise to apply what has been learned in this module about camp closure, and aimed to convey the importance, as well as complexity of the process.

- Solicit any outstanding questions or comments, and then move on to a recap of the key messages.

## Activity 4B –Developing a Camp Closure Action Plan (Extended) – 80’

- Activity 4B follows the exact same outline as 4A above until the slide ‘Group Work’. Then continue and complete the activity with the guidance below.

Show Slide: Group Work – Develop an Action Plan for Closure

- Divide the participants into groups. Assure that each group has representation from the different stakeholder groups, if feasible.

- Distribute 3 pre-prepared flip charts to each group: ‘Action Plan Template’ (based on the matrix on the slide; if groups need additional sheets they can make more as needed.)

- Explain: A Camp Closing Committee, chaired by UNHCR, has been established to lead the development of the closure action plan. Represented in the committee are the relevant stakeholders: the national authority as camp administrator, UNHCR (camp coordination), the agency in charge of camp management (assume for this exercise, it has been delegated to an NGO), refugee and host population representatives, key humanitarian and development organizations.

- State: Your task in this exercise is to assume the role of the closure committee members who have been tasked to draft the action plan.

- Explain: Create a camp closure action plan, based on your actual country context. The plan must ensure that the refugees are protected and assisted and the vacated site is well-managed. Use the pre-prepared flip charts as a template for the plan. Remind the group that a closure plan considers both people and infrastructure, so for each action/activity, indicate which need it responds to.  Also, for each action, identify the responsible actor(s) involved in the closure process. (Reference the “key stakeholder” slide if needed.)

- Tell participants: Focus on capturing all the ideas about what needs to happen to responsibly close the camp. Do not get bogged down in what comes first when recording the items in the action plan. The group can number the items at the end to indicate priorities and/or what needs to happen first. Use the handout to help guide you through issues you need to consider and make them specific to your context.

- Allow 35’ for the groups to work on their action plans.

- Alert the group when there are 5’ remaining in order to wrap up, and number actions to indicate priorities and/or what needs to happen first.

Report Back & Debriefing the Exercise – Allow 30’

- Ask each working group to post their action plan on the wall for all participants to see. Allow a few moments for participants to review the action plans of the other groups.

- Highlight that an actual plan would of course be far more detailed than these draft plans, including timelines, resources needed, specific identification of who is responsible at the activity level, sector considerations etc. (Refer back to the Components of an Action Plan Slide.)

- Ask one group at a time to present 2 items they discussed and included in their action plan and focus on items not presented by the previous group(s).

- If time allows, ask each group to share one more action item that has not yet been discussed during the reporting back.

- Distribute the Handout: Table for Camp Closure Action Plan. Allow a few minutes for participants to review the handout and ask any questions.

- Remind participants to also refer to the handout used during the exercise: ‘Issues to Consider with Guiding Questions & Notes’. We will use these two resources documents, along with the participants’ experience during debrief.

- Facilitate plenary discussion based on the following questions. Include any additional questions that are responsive to the specific context and/or issues raised during the report back.

- Ask: What are the priority issues/action items in their country context and why?

- Ask: What are the biggest challenges for camp closure in their context?

- Ask: What are other actions/issues that were not included in the draft action plans compared to the handouts?

- Ask: Are the missing items oversights? Or are they less important for this context? Why or why not?

- Ask: Are there any items on the Table that are not relevant for your context? Are there issues that need to be considered that are not captured in any of the resource documents?

- Solicit any outstanding questions or comments, and then move on to a recap of the key messages.

## Activity 5 – Review of Camp Closure – 3 ‘

Show Slide – Key Messages

- Review the key messages on the slide and solicit any questions and/or closing comments.

- Thank the group for their participation and hard work!