TABLE for CAMP CLOSURE Action Plan

Component Parts and Guidance Notes

Note that this Table is illustrative, not comprehensive, and must be modified for each context.  Additionally, the ‘Responsible Actors’ column provides general guidance only, but the realities of the specific country context should be applied.

| People | Responsible Actor(s) |
| --- | --- |
| Consult the national level exit strategy: - Serves as a framework for action planning. - Provides guidance on legal issues and policies; is there an MOU? - Points to the level of government commitment to refugee rights and support for DS; is there a tripartite agreement? - Indication of available resources. | UNHCR & government authorities to study in full; Other committee members selectively |
| Review the camp situation analysis: - Data from the situation analysis feeds into the action plan. - Helps to identify gaps. - It may require updates to reflect changes in the context, e.g. is population data current? Does security assessment reflect the current situation, both in the camp and areas of return? - It may require additional information to plan and make informed decisions, e.g. are data profiles detailed enough for protection purpose? Is there adequate information on refugees’ preferred choice for durable solutions? | All committee members, feedback from refugees most important |
| Conduct a planning workshop: - Agree on overall aims and objectives. - Establish outputs and the main activities. - Affirm or clarify roles and responsibilities in the process. - Establish timeframe for the closure process; inclusive of planning preparation time through to rehabilitation, consider all factors e.g. school year, agriculture cycle, rains. - Establish an approximate budget. - Draft a MOU. | Full committee Identify appropriate facilitator for the context |
| Adapt the information management system: - Assure that all stakeholders in coordination and consultation bodies have timely and equal access to data. - Pay particular attention to refugees and the host community, so that they can both contribute to the process, and be informed in a timely manner. | Usually UNHCR, (a coordination function) |
| Ensure coordination mechanisms are in place and understood | All 3 camp response functions |
| Plan resource mobilization | Generally UNHCR (a coordination function) |
| Monitor security, in both the camp and area(s) of return, closely: (this refers to both people and infrastructure) - This is of particularly concern in an insecure context. Degrading security/ insecurity can complicate, slow down or stop the camp closure process. Authorities need to be reminded of their responsibility for law and order on a local and national level. | UNHCR, camp management agencies, refugees, and also the involvement of national authorities |
| Re-assess refugees preferred choice of Durable Solutions, identify main obstacles and potential remedies - Clarity about the progress towards DS is critical. Identify any issues that may require advocacy and/or proactive follow-up. | UNHCR, camp administration function, refugees |
| Develop scale down/phase out plans per sector; integrate into the overall action plan - There may be multiple “action plans or sectoral plans” in development, but these should integrated/ reflected in one overall camp level action plan. | Camp management agencies, humanitarian agencies providing services, UNHCR |
| Mitigate against heightened protection risks of persons with specific needs - Ensure adequate representation for persons with special needs, to reflect their needs in planning and in information dissemination. - Prepare transport and ensure services are continued for residual population (Often persons with specific needs wait until family is settled before joining them.). | UNHCR, refugees, associations in or outside the camp, protection agencies |
| Engage development actors in the camp closure process for repatriation - Development plans should factor into planning as early as possible, as refugees need to restore their livelihoods and have access to services such as health and education. | UNHCR to liaise with UN agencies in country of return; development agencies |
| Follow up on Return & Reintegration Packages - This may impact decisions about DS, so assure adequate information campaign/ dissemination is in place. - Ensure they are resourced and prepared for timely delivery. | UNHCR, camp management agencies |
| Movement Logistics | UNHCR, government authorities on both sides of the border |

| Infrastructure | Responsible Actor(s) |
| --- | --- |
| Update inventory list of assets and facilities in use by camp: - Include handover considerations: future use of assets and infrastructure, what needs upgrades or demolition. | Camp management in consultation with authorities (local or national, as appropriate) |
| Develop guidance on compensation for clean up | Camp management in consultation with refugees, Host community/authorities |
| In accordance with exit strategy, organize handover documentation - Develop a written plan for data handover to the relevant departments, e.g. social service, education and health, to ensure the population can access necessary documents (identification, vaccination and school records, etc.) upon return. | UNHCR, camp management and host authorities |
| Agree what access the residual population will have to services handed over | UNHCR, camp management, host authorities, refugees and service providers |
| Organize demolition, pit filling and waste disposal in a manner that prevents harm to people and the environment | UNHCR, host authorities, with camp management |
| Plan for restoration of camp area after vacating which aims to leave behind an improved and environmentally healthy area | UNHCR, host authorities, with camp management |
| Establish security plan to guard against looting of assets | UNHCR, host authorities, with camp management |
| Plan for the monitoring and reporting of the closure process, inclusive of capturing lessons learned | UNHCR and camp management |