# Developing a Camp Closure Action Plan: Issues to Consider with Guiding Questions & Notes

Key Points to Remember

- The action plan must consider the needs of people and infrastructure.

- The components of an action plan include: defined objectives, deliverables, roles & responsibilities, required resources, timelines and sector considerations.

- The process requires full and equal participation of all parties; assure representation and inclusion across genders, ages, different groups and persons with special needs.

- The key stakeholders are: CA, CCC, CMA, camp residents, host community, and humanitarian/development actors.

| CONSIDERATIONS |  |
| --- | --- |
| Issue to Consider | Guiding Questions & Notes |
| DURABLE SOLUTIONS | What choices do IDPs have? How can durable solutions best be advanced and by whom? - Remember the three options available to displaced: return to their place of origin, integrate locally, in the area where they have been displaced, or settle elsewhere in the country. - Remember the principles that guide Durable Solutions: return must be voluntary; IDPs have the right to make free and informed choices; and the right to participate in the planning and management of that choice. |
|  | What guidance does the national exit strategy provide? - What commitments, if any, have been made by the government to support durable solutions? Does a MoU exist or any other agreements? - Are there any legal provisions for restitution and compensation? - Are IDPs well informed about their existing rights and applicable policies? |
|  | Ensure accurate information is available for different groups within the IDP community. - Some options include: organizing ‘go and see’ visits & information campaigns. - Facilitating interaction between IDPs and government authorities to negotiate practicalities of government support to a chosen option, e.g. allocating land and providing basic infrastructure; mechanisms to assure security, etc. - Encourage IDPs to form committees, where the different community members can become aware and discuss their rights and responsibilities, formulate strategies to have their rights respected and fulfilled and organize compliance with their obligations such as submitting accurate information, provide labour as required for the closure process, protect vulnerable members. |
|  | What choices and decisions have been made? It is important to work closely with the camp population and the host community, to determine what durable solutions individuals in the camp have decided. This will form the basis of determining the direction of camp closure: - How many people have intended to locally integrate? What are the implications for the local population? - Is there a residual population which intends to stay at the camp site? What needs to happen to develop it into a viable functioning community? - For those who are returning, or resettling, how will their situation be monitored? What steps need to be taken to prepare the areas of return for a viable future for the displaced? |
|  | What are the concerns of the population who are returning or resettling? Are the areas of return secure? What is the level of damage due to conflict or disaster? What about livelihoods? Engage government development bodies to refocus their development plans on the return and the potential resettlement areas. Invite national and international development organizations to consider livelihoods rehabilitation support in these regions. Facilitate interaction with Early Recovery cluster, humanitarian actors about start up support and early recovery activities in the new/home location. |

| LEGAL | How will legal issues be addressed? Use the national exit strategy and the national MoU to provide guidance for addressing legal issues. The role of the government needs to be clearly defined. |
| --- | --- |
|  | Some examples of legal issues to be considered are: Who has access to the land and buildings? Replacement of lost documentation (identify cards, land titles). Management of children born in the camp and issuance of birth certificates. |
| SECURITY | What are the security protocols and plans needed to ensure the safety of residents, staff and the community during the camp closure process? |
| CONSIDERTATION & RESTITUTION | In principle, the national level consultation should provide the parameters for issues of compensation and restitution. Cautionary note: Managing this issue requires sensitivity, given its potentially contentious nature. Every effort must be made to prevent negative repercussions for IDPs. |
|  | Restitution should ensure equal access for men and women; a consultative body should work at the camp level with relevant actors to achieve this. |
|  | Are there any land compensation issues to consider? This should be decided at the national level and reflected in the local action plan. A clear agreement about land compensation is essential, including good communication to ensure all stakeholders are informed. |
|  | Will there be any compensation packages issued? Any decisions on additional compensation which may be provided to other stakeholders (such as the host population) should be decided at a national level. |
| LAND OWNERSHIP | What will be done with the land after closure of the camp? The owner needs to be included in discussions to ensure decisions and plans are coordinated. Local agreements should be established accordingly. |
| DE-REGISTRATION | When displacement is coming to an end, a process of de-registration or documenting the departure of the IDPs is required. Where IDPs are already registered, de-registration should take place. In the absence of registration, make efforts to document their departure. In either case, it is important to consider any residual population. |
| PROTECTION | What are the needs arising from the closure process? What is in place to meet these needs? What is missing and has to be organized? |
| IDPs AND RESIDUAL POPULATION | What must be done to ensure protection for all residents in the closure process? To effectively respond to protection concerns, you need an updated accurate profile of the camp population, disaggregated by gender, age and identify the vulnerable and persons with special needs. The needs of the residual population should also be accounted for in the plan, including a monitoring process to ensure access to services after closure. |
|  | What is best closure strategy in order to assure protection and assistance to IDPs? e.g. a rapid departure or a gradual exit? How are services maintained during the transition? Is there sufficient monitoring capacity to avert protection risks inherent in a rapid movement? |
|  | What are the protection considerations in each relevant sector? These need to be included the respective sector plans. For example, what will people eat once distribution is discontinued? How is health care continued during and upon return? What provisions are made to ensure there is necessary medication at the locations of return? |
| INFORMATION MANAGEMENT & COMMUNICATION | Why are intense communication and a well-managed information flow so important for a smooth process of closure? What do you need to put in place to ensure that flow? |
|  | Consider the various levels of communication, such as the national and local level and how to facilitate communication between them. What are the needs and issues at the different levels? How can agreement be reached to respond effectively to competing /conflicting needs? |
|  | What about data collection? What information is needed and how do you assure accurate information? What mechanisms are needed to track all the necessary data? |
|  | What are some strategies to facilitate the exchange of information and open dialogue? You need to have venues, consultative bodies in place where partners can meet, communicate and coordinate. A camp closure committee is one example. Organizing IDP committees can help bring together diverse groups, where specific issues can be raised and brought to the closure committee for action. |
|  | What information dissemination strategies are needed? What feedback loops are built into these mechanisms? Has the media been considered as part of the strategy? Good communication means access to information for all as well as means to contribute to the dialogue. Methods need to be accessible, easy to understand by all, and promote common understanding, transparency and accountability. Consider the needs of the illiterate; language differences & marginalized groups. Also consider location: where is information posted and made available? How does that impact access for all groups? Possible mechanisms to respond to these concerns include: use of local radio; suggestion/complaint desks to submit verbal input; information campaigns which use symbols, multiple languages etc. |
|  | Are there any advocacy needs? What are they and how can they be addressed? |
| RETURN & REINTEGRATION PACKAGE | Does the national plan provide guidance on any return & reintegration packages? National level policy regarding return packages will be implemented at the local level and must be reflected in the action plan. IDPs need to be informed as return packages may impact their choice of durable solutions. |
| MOVEMENT LOGISTICS | What support, if any, will be afforded to IDPs to return or resettle? What protection issues must be considered? |
| TRAINING | Does the population require any training opportunities prior to departure? Possible topics include conflict management, rights training; or specific livelihood skills which may be useful in the area of return or resettlement. |
| DOCUMENTATION HANDOVER | What kind of documentation, if any, needs to be handed over to relevant departments? For example, immunization cards to the Health Dept, education records or proper identification to ensure access to services upon return. All sensitive data must be handled confidentially and in line with data protection principles in order to safeguard the right to privacy. |

| INFRASTRUCTURE CONSIDERATIONS |  |
| --- | --- |
| Issue to Consider | Guiding Questions & Notes |
| SECURITY | Establish plan to ensure security of the vacated site, to minimize risk of theft and related damage. |
| DECOMMISSIONING | What action is required to decommission and close the camp? The national exit strategy should be consulted first for legal considerations and applicable policies. Decommissioning must be carried out as swiftly as possible following the departure of the camp residents. An MoU/agreement is recommended. |
|  | Determine compensation modalities for cleanup activities. |
|  | What decisions need to be made in terms of the remaining infrastructure? What may require dismantling? |
|  | Waste and other now useless material and installations must be removed and safely disposed of, ensuring the safety of people and the environment (e.g. filling latrines etc.). |
| HANDOVER & FUTURE USE OF ASSETS | Identify handover modalities between the relevant stakeholders, particularly the government and host community. |
|  | Outline who is responsibility for future management of assets to ensure sustainability and make issues of ownership clear. |
|  | Handover should be formalized in a written agreement with clear roles and responsibilities. |
| INRASTRUCTURE FOR UPGRADE OR DEMOLITION | Are there any materials that can be salvaged and recycled for future use? |
|  | Are there any opportunities to improve and/or upgrade facilities? Would they tie in with the country’s national development plan? |
|  | Do temporary/semi-permanent shelters have items that the displaced population can dismantle and take for use in their respective areas of resettlement (e.g. doors, beams, roofing material)? |
|  | Do plans need to be drawn up for timely removal of items to prevent looting and/or unauthorized use of recyclable materials? |

| HANDOVER OF SERVICES & RESPONSBILITIES | What will be the future function of the camp? Will there be a residual population? |
| --- | --- |
|  | What services if any, need to be handed over? Who will be responsible? This is generally taken on by local leadership or national authorities. However, liaising with relevant humanitarian and development actors should also be considered. |
| REHABILITATION | What are the rehabilitation needs of the former camp site? Are there any negotiations about rehabilitation and extent of upgrading needed to make these determinations? What are the budget considerations? |
|  | What camp clean-up processes are needed, inclusive of environmental rehabilitation? |
| INVEN-TORY | Is the inventory of assets and facilities up to date and complete? |
|  | If none exists, what steps need to be taken to create an inventory? |
|  | What will be the determination of each? Discard? Recycle? Handover? Etc. |
| ENVIRONMENT | What are the environmental impacts to consider -- both in terms of the camp’s existence at the site, and the future impact of closure? The answer should be based on assessments that involve the relevant stakeholders, as well as the geography and livelihoods of the area. The information should then feed into rehabilitation of the site. |
|  | Community self-help and engagement is a useful strategy to address environmental impacts: a one-time assistance package can be provided in exchange for future agreed upon activities which support environmental management and rehabilitation. Reforestation and nursery activities are a common example. |

| OVERARCHING CONSIDERATIONS: People & Infrastructure |  |
| --- | --- |
| Issue to Consider | Guiding Questions & Notes |
| MOVE TOWARDS DEVELOPMENT | The plan should outline the eventual move towards development and thus include activities relevant to the context and indicate any overlap between humanitarian and development actors. |
|  | This is an opportunity to improve on existing structures and local and national authorities should be consulted and actively participate; ideally, these discussions can begin well in advance. |
|  | Special attention should be given to possible weak linkages between humanitarian response activities and long term sustainable development plans. |
| MONITORING & REPORTING | How will the implementation of the plan be monitored? The plan can include a specific monitoring section, and/or Monitoring can be explicitly addressed within activities. |
|  | Establish a feedback mechanism. Ensure that IDPs have continual opportunity to feedback; and that the plan has the flexibility to be revised as needed to reflect changes on the ground. |
|  | How will reporting and documentation of the process be handled? |
|  | Is there a mechanism to capture lessons learned? |