Site Closure

MODULE 12

Introduction

This module analyses the main reasons for closing sites and explores long-term solutions for IDPs and refugees who have been displaced, in particular the principles that should guide the development and implementation of exit plans. The module considers the Camp Management team responsibilities throughout this process, in view of the actions to be planned for the physical closure of the location itself.

It is thematically linked to:

- Module 2: Roles & Responsibilities

- Module 3: Humanitarian Principles

- Module 11: Site Improvement and Design

Module at a glance:

| Topic / Activities | Description | Time (min) | Resources |
| --- | --- | --- | --- |
| 1. Site closure quiz Activity 1 | Presentation on: - Objectives Group work on: - Site closure true/false quiz | 45 | PPT Print Annex 12.1 |
| 2. Considering the guiding principles Optional Activities 2A or B |  | 60 |  |
| Activity 2A | Group work on: - The Framework for Durable Solutions |  | Print Annex 12.2 Print Annex 12.3 |
| Activity 2B | Presentation on: - Ending displacement |  | Print Annex 12.2 Print Annex 12.3 |
| 3. Plan the CMA responsibilities in the closure process Activity 3 | Group work on: - Responsibility matrix | 30 | Flipcharts Post it notes |
| 4. Site closure and return Activity 4 | Group work on: - Dos and don’ts for camp managers | 30 | Print Annex 12.4 |
| 5. Intention surveys Activity 5 | Presentation on: - Camp life cycle and durable solutions | 10 | Flipchart Print Annex 12.5 (optional) |
| 6. Site closure process Optional Activities 6A or B |  |  |  |
| Activity 6A | Group work on: - Developing an action plan for closure | 45 | Print Annex 12.6 |
| Activity 6B | Role play on: - Presenting an action plan to national authorities | 60 |  |
| Total Activity timeframe |  | 210 – 235 minutes |  |

Contextualisation and adaptation tips

| Activity | Adaptation tip |
| --- | --- |
| Activity 1 | The quiz exercise will allow the trainer to assess participants’ understanding of both durable solutions and the site closure process to identify what is the missing content that participants need to build up and expand during the session if they have a low level of understanding. Alternatively, the quiz activity can be used at the end of the module to reinforce the content covered during the module as a closing activity. |
| Activity 2 | Activity 2A is recommended for operational contexts. Activity 2B is recommended for preparedness contexts. An alternative debriefing option for activity 2 is to divide into three groups. Instruct them to choose group rapporteurs. Prepare three flip chart papers and focus the discussion as follows: Group 1 will discuss what considerations need to be made concerning the views of the Camp Residents (IDPs/refugees) by the Government and the CM. Group 2 will discuss what considerations need to be made concerning the Host Community concerning the camp closure. Group 3 will focus on considerations concerning the Camp Infrastructure to be made by the camp management agency. Ask the rapporteurs to report in Plenary on flip chart papers. Once done, ask the participants in the plenary will make short presentations and provide their ideas on what might have been specific actions that were missed out / omitted by the CM and the Government during the closure process specific to the 3 concerned groups (Camp Residents, Infrastructure and Host Community). |
| Activity 6 | Activity 6A is recommended for operational contexts. Activity 6B is recommended for preparedness contexts. If sites were planned in Module 11, an alternative exercise is to have participants close the sites that were planned in activity 2B. To do this, instruct the participants to return to their groups. Remind them that planning for camp closure should be done from the very beginning of camp set up. Participants will now have to close the camps they set up in Module 11. Provide them 20 minutes to make a closure and exit plan, ensuring where durable solutions principles and practices are applied. Provide them a closure planning template on a flip chart paper. Allow each group 10 minutes to present their plan to the plenary. Make a gallery presentation where other groups can comment/pose clarifications. Follow this with the site closure checklist Annex 12.4. |

Module Key Messages

- The closure activities of a camp are a context-specific process.

- Planning for exit and closure of the camp is best taken as an integral part of the set-up process.

- The Camp Management Agency, in coordination with the Cluster/ Sector Lead Agency, plays a facilitating role in conducting training and/or disseminating information at the camp level concerning durable solutions.

- Whatever the circumstances around camp closure, careful planning and extensive coordination is crucial and should be carried out by the Camp Management Agency in collaboration with national authorities and other key stakeholders.

- A durable solution is achieved when IDPs no longer have specific assistance and protection needs that are linked to their displacement and such persons can enjoy their human rights without discrimination resulting from their displacement.

- A principal task of a Camp Management Agency is to work with key stakeholders in the camp response, to ensure the identification of durable solutions for the camp population as well as assess the intentions of the camp residents.

- Facilitate go-and-see visits including women, children of a certain age and level of maturity, persons with special needs and persons who are potentially marginalised.

- Spontaneous return may be triggered by changes in the home areas or in the areas of displacement, also includes people choosing to return on their own rather than as part of agency-organised return programmes.

- Forced return take place when pressure by authorities is exerted to have people return to unsafe areas.

- Intention surveys provide a good overview of IDPs’ future plans and preferred choices in relation to long-term solutions, including their perceptions about the general situation back home, existing issues and concerns related to their life in displacement and the main aspects preventing them from leaving the site.

- States have the primary duty to establish conditions which allow displaced persons to benefit from durable solutions voluntarily, and in safety, security and dignity.

- Site closure action plans are built based on a National Exit Strategy that provides the overall approach, context and principles for phasing out camp-based assistance. Local/site closure action plans shall elaborate on: people elements, infrastructure aspects and also support/operational activities.

- 1. Introduction to Site Closure

Learning objective

Assess participants’ understanding of the concepts related to site closure.

Preparation and materials

- Set up projector

- Edit the objectives slide to fit the activities included in the session

- Flipchart and markers for the trainer

- Pads of paper and pens for the participants

- Review the quiz to be sure you are familiar with the animation of the slides and answers to each of the questions

- Print Annex 12.1 T/F quiz answer key for the trainer, if using the quiz

- Prize for the team that gets the most correct answers on the quiz

Facilitator’s tip: The quiz can be used at the beginning of the module to gauge the knowledge level of the participants or at the end of the module to assess knowledge gained.

Duration:										  	45 min

| Slide | Instructions |  |
| --- | --- | --- |
| Why do sites close? (header slide) Why do sites close? (text slide) | - Ask: Why do sites close? Brainstorm in plenary and write the suggested ideas on a flipchart. Possible responses include: - People spontaneously leave - There is a durable solution in place - Security threats - Government coercion - Other transitional solutions are required - Assistance and service provision phased out - Housing, land and property issues - Ask participants to share their experiences from other operational settings. Reveal the indicators on the slide and note those that were identified by the group and discuss the indicators that were not identified. |
| Objectives | - Anticipate the session and affirm the answers about why sites close by presenting the objectives of the session. Explain that this session will explore issues related to closure specific to their context, but in general site closure has both long-term resolutions which are addressed at a political and policy level as well as practical actions which relate to operational activities in sites which need to be done in accordance with humanitarian standards. |  |
| The camp life cycle Types of camp closure | - State: Camp closure is an integral and inevitable part of the camp life cycle - Remind participants that the term ‘camps’ is used throughout the module for simplicity, but is intended to represent all types of settlements, including collective centres. - Highlight how camp closure is usually differentiated by two opposing factors – forced/spontaneous or planned/organised closure. Ideally, the process is gradual and follows indications that IDPs are ready to return, relocate or resettle in places of their preference. The closure process should be planned for in advance, with planning for closure from the start of providing services in a temporary site. - Planning for closure is a context specific activity and can be the result of a variety of indicators. |  |
| Test your knowledge! Quiz slides 1 through 10 | - Organise the group into small teams or pairs to take the quiz. Explain that the quiz will test their knowledge on site closure. They should write down their answer on a paper. NB! The questions of the quiz are revealed one by one on the slides with the answer and explanation following. - Show slides on the T/F quiz. The answer is part of the animation. - Planning for exit and phase out of the site is an integral part of the site closure phase. A: FALSE, planning for exit and closure of the camp is an integral part of the set-up process. Show the camp life cycle. - Camp closure is a context-specific process. A: TRUE. Provide/ask for examples. - Closing a camp means ending displacement. A: FALSE. Ending displacement is a long term process that requires regaining access to rights that were deprived during displacement. - A camp only closes when there is a durable solution in place. A: FALSE. A camp can also close when assistance and service provision phase out, if there are security threats, due to government coercion or because another transitional settlement solution is required. - A displaced person will find a long-term solution to their displacement by settling with their relatives in a safe place. A: FALSE. According to the Framework for durable solutions: A durable solution is found when a displaced person no longer has specific assistance and protection needs linked to his/her displacement situation. The search for durable solutions is: - A gradual, often long-term process of reducing displacement-specific needs and ensuring the enjoyment of human rights without discrimination; - A complex process that addresses human rights, humanitarian, development, - reconstruction and peace-building challenges; - A process requiring the coordinated and timely engagement of different actors. - Internally displaced persons have three long-term options: return (going back to their place of origin or habitual residence), local integration (settling permanently in their place of refuge) or settlement elsewhere (starting a new life somewhere other than their place of origin or refuge). A: TRUE. Durable solutions for IDPs are explained in the Guiding Principles on Internal Displacement and developed further in the Framework for Durable Solutions. - The camp management team needs to train and/or disseminate information about durable solutions at camp level. A: TRUE. Effective communication strategies, such as communication campaigns and referring information gaps to humanitarian service providers, should be put in place so that the displaced population can make informed decisions. These campaigns may include information on available solutions, services and facilities available in the host community, solutions for vulnerable people and means to access assistance. The information must be provided in a language and format understood by the IDPs, including those who are not literate. Where IDPs are in urban areas or dispersed settlements, special efforts will be needed to ensure that they receive notice of consultations and information. - The camp management team needs to promote the protection of persons with specific needs (e.g. GBV survivors) and people staying behind. A: TRUE. Particular attention needs to be paid to vulnerable cases, and there will be groups at risk who will require special assistance when leaving the camp. The Camp Management Agency also needs to estimate the number of individuals and families staying behind and monitor the continued service provision to them to ensure that their needs are met. The agency can do this by: - establishing adequate referral mechanisms and case management structures within the Camp Closure Action Plan; - ensuring that departure zones have a separate area designated for groups at risk and their family members; - encouraging persons with special needs to return with extended family members, women or groups of families accustomed to living together. - The camp management team needs to stop forced return processes, putting camp leaders at the forefront of this effort. A: FALSE. The camp management team can advocate against forced return and collaborate with the protection partners to show evidence of such practices. The CMA need to ensure Do No Harm and avoid exposing camp populations to further risks. - The camp management team needs to prevent displaced persons from visiting the resettlement areas in order to ensure people’s safety and security. A: FALSE. Planning go-and-see visits is an activity through which camp residents exercise their right to participate in and be informed about the return, resettlement or integration process. Including women, children of a certain age and level of maturity, persons with special needs and persons who are potentially marginalised. - Provide the more in-depth reflection on the answers to the true/false questions in plenary and resolve any new inquiry. Ask differing opinions to be defended and to provide the rationale behind the answers. Use the background information and examples for the participants based on operational experience and related to issues in the training context related to site closure. - Give the winners of the quiz a prize! |  |
| Key messages | Recap on key messages: The closure activities of a camp are a context-specific process. Planning for exit and closure of the camp is best taken as an integral part of the set-up process. ## The Camp Management Agency, in coordination with the Cluster/ Sector Lead Agency, plays a facilitating role in conducting training and/or disseminating information at the camp level concerning durable solutions Facilitator’s tip: Ask the participants to discuss the key message before changing slide from photo to message. |

- Considering the guiding principles

Activity 2A: Applying the Framework for Durable Solutions

Learning objective

Analyse the application of guiding principles in the training context.

Preparation and materials

- Identify a training participant in advance to present to the group. Help them prepare a short presentation of approximately 15 minutes on topics related to site closure relevant to the training context and on the operational plans for the national, regional or locality for site closure. The choice of speaker will depend on the learning needs of the group and could include either long-term solutions to displacement or plans for site closure.

- Print and cut apart the cards in Annex 12.2: Question cards for each group.

- If the IDP Guiding Principles information is included, also print copies of Annex 12.3: IASC Guiding Principles Quick Reference Guide.

Facilitator’s tip: Activity 2A is recommended for operational contexts. If there is a high degree of knowledge in the training room on the IDP GPs, this information can be omitted and 15 minutes reduced from the presentation.

Duration:										  	60 min

| Slide | Instructions |
| --- | --- |
| Guest lecture The Guiding Principles Durable Solutions | - Introduce the speaker. Have him/her present their knowledge relevant to the training setting. Ask participants to note down the most relevant points of the exit plan for their role. (Allow the speaker to present for approximately 15 minutes) - The Guiding Principles on Internal Displacement are the recognised framework for camp closure for IDPs. Their emphasis on “sovereignty as responsibility” puts the responsibility of closure on the authorities. It also emphasises the participation of IDPs in decisions that affect them. Principles 28-30 provide guidance on return, resettlement and reintegration: - Principle 28: Competent authorities have the primary duty and responsibility to establish conditions to allow IDPs to return voluntarily and facilitate the reintegration of returned or resettled IDPs, and to ensure the full participation of IDPs in the planning and management of their return, resettlement and reintegration. - Principle 29: IDPS who have returned or resettled shall not be discriminated against as a result of their displacement. Competent authorities have the duty and responsibility to assist IDPs to recover, to the extent possible, their property and possessions which they left behind or were dispossessed of upon their displacement. - Principle 30: All authorities concerned shall grant and facilitate for international humanitarian organizations and other appropriate actors rapid and unimpeded access to IDPs to assist in their return or resettlement and reintegration. |
| Group work | - Organise the plenary in three groups and provide them with a set of 3 cards (printed from Annex 12.2). - Instruct them to review their card, which includes a question related the principles provided in the Framework for Durable Solutions. The groups are to discuss whether this has been applied in their context: - Do national authorities assume the primary responsibility to provide durable solutions for IDPs? - Do the authorities concerned grant and facilitate rapid and unimpeded access to humanitarian and development actors that assist IDPs in achieving a durable solution? - Have relevant authorities taken the needs, rights and interests of IDPs as primary considerations guiding all policies and decisions on durable solutions? - Can IDPs make an informed and voluntary choice on what durable solution to pursue? - Do all relevant actors respect and agree upon the right of IDPs to participate in the process of planning and implementing the durable solutions? - If return becomes a feasible option, IDPs’ choice of local integration or settlement elsewhere in the country must not be regarded as a renunciation of IDPs’ right to return. Is this the case? - Under no circumstances should IDPs be encouraged or compelled to return or relocate to areas where their life, safety, liberty or health would be at risk. Is this the case in your context? - Are IDPs who are seeking a durable solution neglected or discriminated against for reasons related to their displacement? - Will the IDPs who achieve a durable solution continue to be protected by international human rights and, where applicable, humanitarian law? - Allow 20 minutes. Where the answer is negative, encourage the groups to provide a way forward to contribute to meeting the Framework and readdress the issue from their own respective roles. They should reflect on their experiences as well as the experience presented by a peer at the beginning of the session. |
| Key message | ## Recap on key message: Whatever the circumstances around camp closure, careful planning and extensive coordination is crucial and should be carried out by the Camp Management Agency in collaboration with national authorities and other key stakeholders. A durable solution is achieved when IDPs no longer have specific assistance and protection needs that are linked to their displacement and such persons can enjoy their human rights without discrimination resulting from their displacement. Facilitator’s tip: Ask the participants to discuss the key message before changing slide from photo to message. |

Activity 2B: Discussing the Framework for Durable Solutions

Learning objective

Analyse the application of guiding principles in the training context.

Preparation and materials

- Identify a training participant in advance to present to the group. The speaker should prepare to speak for 15 minutes and present experiences in camp closure due to camp consolidation, forced return, etc. If the training is in a preparedness setting where the national, regional or local plans are developed, these plans could also be presented depending on the relevance of the topic to the group and include long-term solutions to displacement or plans for site closure.

- Print and cut apart the cards in Annex 12.2: Question cards for each group

- Print Annex 12.3: IASC Guiding Principles Quick Reference Guide if needed

Facilitator’s tip: Activity 2B is recommended for preparedness settings.

Duration:										  	60 min

| Slide |  | Instructions |
| --- | --- | --- |
| Guest speaker holder slide |  | - Introduce the speaker. Have him/her present the camp closure plans in the training setting. Ask participants to note down the most relevant points of the exit plan for their roles. |
| Durable solutions |  | - State: Whatever the specific circumstances that prompt the closure of a camp, we have a duty to close the camp as responsibly as possible within the specific context. - Ask for a volunteer to read the slide aloud and reflect about its meaning. - Remind participants that closing a camp does not mean the end of the displacement nor that durable solutions have been found. |
| Durable solutions: Refugees and IDPs |  | - State: Durable Solutions are pursued for both refugees and IDPs. - Ask: What is the difference between refugees and IDPs regarding their choices for durable solutions? Take a few answers from participants, then highlight and recap the choices for internally displaced populations. - Link back to the profiles that were created at the beginning of the training as a way of providing linkage to previous sessions and the global overview of internal displacement. - Explain: It is important to understand that durable solutions are a parallel process that in reality may not be part of the camp closure/decommissioning process itself. While durable solutions ideally trigger camp closure, these are two different processes. However, actors responsible for camp closure need to be aware of the extent to which the process of durable solutions for the camp population is advancing. This information is a decisive factor for planning closure. |
| When does displacement end? |  | - Building upon the presentation, elaborate that the Durable Solutions Framework is an international tool/document that aims to provide guidance for achieving durable solutions following internal displacement in the context of armed conflict, situations of generalised violence, violations of human rights and natural or human-made disasters. Being of a generic character, the Framework needs to be applied in light of the specific situation and context. - The purpose of the Framework is: - To foster a better understanding of the concept of durable solutions for the internally displaced; - To provide general guidance on the process and conditions necessary for achieving a durable solution; and - To assist in determining to what extent a durable solution has been achieved - Ask: based on their experience what would some of the specific contextual issues that would need to be considered? Take a few answers from the group. If appropriate refer to the case study used in the previous sessions and ask what would need to be applied for that camp context. |
| Principles to guide durable solutions |  | - Explain: The search for durable solutions is a complex, often lengthy process designed to restore the human rights of displaced populations. Many actors are involved (primarily authorities) who need to observe a number of key principles to make the quest for durable solutions a success. - The process to support durable solutions should be inclusive and involve all parts of the displaced population, including women, children, persons with special needs and persons who are potentially marginalised. - It’s a rights-based process where national and local authorities, humanitarian and development actors need to work together to effectively support IDPs |
| Guiding Principles on Internal Displacement |  | - Review principles relating to return, resettlement and reintegration: - Principle 28: Competent authorities have the primary duty and responsibility to establish conditions to allow IDPs to return voluntarily and facilitate the reintegration of returned or resettled IDPs, and to ensure the full participation of IDPs in the planning and management of their return, resettlement and reintegration. - Principle 29: IDPS who have returned or resettled shall not be discriminated against as a result of their displacement. Competent authorities have the duty and responsibility to assist IDPs to recover, to the extent possible, their property and possessions which they left behind or were dispossessed of upon their displacement. - Principle 30: All authorities concerned shall grant and facilitate for international humanitarian organizations and other appropriate actors rapid and unimpeded access to IDPs to assist in their return or resettlement and reintegration. |
| Group work | - Divide the plenary into groups to discuss measures that could guarantee that the principles are respected and promoted. Give each group a set of cards from Annex 12.2 to drive their discussions. - Do national authorities assume the primary responsibility to provide durable solutions for IDPs? - Do the authorities concerned grant and facilitate rapid and unimpeded access to humanitarian and development actors that assist IDPs in achieving a durable solution? - Have relevant authorities taken the needs, rights and interests of IDPs as primary considerations guiding all policies and decisions on durable solutions? - Can IDPs make an informed and voluntary choice on what durable solution to pursue? - Do all relevant actors respect and agree upon the right of IDPs to participate in the process of planning and implementing the durable solutions? - If return becomes a feasible option, IDPs’ choice of local integration or settlement elsewhere in the country must not be regarded as a renunciation of IDPs’ right to return. Is this the case? - Under no circumstances should IDPs be encouraged or compelled to return or relocate to areas where their life, safety, liberty or health would be at risk. Is this the case in your context? - Are IDPs who are seeking a durable solution neglected or discriminated against for reasons related to their displacement? - Will the IDPs who achieve a durable solution continue to be protected by international human rights and, where applicable, humanitarian law? |  |
| Key message |  | ## Recap on key message: Whatever the circumstances around camp closure, careful planning and extensive coordination is crucial and should be carried out by the Camp Management Agency in collaboration with national authorities and other key stakeholders. A durable solution is achieved when IDPs no longer have specific assistance and protection needs that are linked to their displacement and such persons can enjoy their human rights without discrimination resulting from their displacement. Facilitator’s tip: Ask the participants to discuss the key message before changing slide from photo to message. |

- CMA responsibilities in the closure process

Activity 3: Responsibility matrix

Learning objective

Plan the responsibilities of a CMA in the closure process.

Preparation and materials

- Prepare 5 flipcharts with the headings for the matrix:

  - Data Collection

  - Protection

  - Coordination and monitoring

  - Participation of the population

  - Communication

- Post it notes

Duration:										  	30 min

| Slide | Instructions |
| --- | --- |
| Group work | - Organise participants into 5 small groups (based on their profiles and expertise). Assign each group 1 responsibility (Data collection and IM, Protection, Coordination and monitoring, Participation, Communication). Pass each group a sheet of flipchart paper. - NB: Depending on the setting, coordination and monitoring can be either considered together or separately. - In their groups, the participants should reflect on what a CM team working in the site needs to do related to these issues. Their answers should also note who they might need to engage with. Groups should be encouraged integrate GBV prevention or mitigation tasks in this exercise to ensure safety to all groups living in the camp throughout the closure process - After 20 minutes of working on their flipchart paper, each group should have completed their section of the matrix. |
| Responsibility matrix | - As the small groups come up with answers to their questions, have them build a life size diagram on the wall with flipchart paper. The slide shows the format to hang the papers together to create a matrix. - Debrief by summarising main points. Answers will be context specific depending on the legal status and type of camp management systems. However, planning for exit and closure from the set-up phase is a key responsibility of a camp management team. Plans presented on the flip charts should be specific. - For example, the types of data to collect that is important to closure includes: - people with specific needs and the nature of their vulnerabilities; - number of residual population remaining in the camp through registration or verification exercises; - detailed camp layout for site rehabilitation and decommissioning; - documentation needs; - security and land ownership issues; - reporting on closure-related problems. - Residing in the camp is a temporary measure with the continuous goal of reaching durable solutions to displacement. Handover plans and agreements with all stakeholders should be in place from the beginning phase of the camp life cycle. - Who should be involved? Who might need to be consulted? Coordination and monitoring This can mean liaising with on-site authorities on behalf of humanitarian actors and services providers in specific camps; consulting with the host and displaced populations, including women and other at-risk groups, taking into consideration GBV-related risks. Communicating with the camp population and implementing information campaigns Effective communication strategies, such as communication campaigns, should be put in place so that the displaced population can make informed decisions. These campaigns need to include information on available solutions, services and facilities available in the host community, solutions for vulnerable people and means to access assistance. - Safety and security issues: Assessing the voluntariness of return or resettlement Voluntary choice means that the displaced population is not pressured into accepting an option. Additional measures are voluntariness are levels of acceptance of proposed durable solutions, return intentions and timing. Promoting protection of persons with specific needs This might include the elderly, persons living with disabilities) and groups at risk (e.g. GBV survivors). Referral systems should be available throughout the closure process. - Good programming issues to consider: Integrating GBV prevention and mitigation into site closure Site closure can increase risks for GBV, and prevention and mitigation measures are integrated into planning as a responsibility of the CMA. The returning/resettling/residual population should be monitored with a particular focus on the safety of women, girls and other at-risk groups. For this purpose, conduct specific training for all camp staff on GBV risks and PSEA related to return/ relocation. GBV specialists should work with relevant government ministries and civil society organisations to ensure continued delivery of services to GBV survivors who are exiting camps. Wherever possible, identify referral systems for their care and support. Data protection failures can put GBV survivors at increased risk. Ensure that safe and ethical systems for the transfer of data—including confidential personal records of GBV survivors—are put in place by organisations and authorities involved in camp closure and return/resettlement/reintegration programmes (with due consideration of the survivor’s best interests and in keeping with the principles of GBV reporting and information sharing). Populations affected by camp closure must have access to information to inform their decisions. Conduct communication campaigns to inform affected populations of camp closure processes and potential GBV risks. |
| Key messages | ## Recap on key messages: A principal task of a Camp Management Agency is to work with key stakeholders in the camp response, to ensure the identification of durable solutions for the camp population as well as assess the intentions of the camp residents. ## Facilitate go-and-see visits including women, children of a certain age and level of maturity, persons with special needs and persons who are potentially marginalised. Facilitator’s tip: Ask the participants to discuss the key message before changing slide from photo to message. |

- Site closure and return

Activity 4: Dos and don’ts for camp managers

Learning objective

Discuss how the CMA could support the situation based on the guiding principles.

Preparation and materials

- Print Annex 12.4: Site Closure Checklist for all participants

- Prepare two flipcharts one labelled Dos and a second labelled Don’ts. Place them at the front of the room.

Duration:										  	30 min

| Slide | Instructions |
| --- | --- |
| Group work | - Draw the participants’ attention to the two prepared flipcharts in front of the room. Ask participants to discuss at their table for 5 minutes: “What should you do and not do as a camp manager related to camp closure.” - After the 5 minutes of discussion, take a suggestion from each table and write them on the appropriate flipchart, compiling all the suggestions from the group. - Reinforce these points by providing relevant examples from different operational contexts related to camp closure. - Distribute Annex 12.4: Site closure checklist. |
| Key message | ## Recap on key message: Spontaneous return may be triggered by changes in the home areas or in the areas of displacement, also includes people choosing to return on their own rather than as part of agency-organised return programmes. ## Forced return take place when pressure by authorities is exerted to have people return to unsafe areas. Facilitator’s tip: Ask the participants to discuss the key message before changing slide from photo to message. |

- Intention surveys

Activity 5: Camp life cycle and durable solutions

Learning objective

Discuss intention surveys and how participants have used them.

Preparation and materials

- Flipchart to take notes of the discussion (optional)

- Print Annex 12.5 DTM Household Intention Survey Report (optional)

Facilitator’s tip: Use this activity in operational settings where returns have not yet taken place.

Duration:										  	10 min

| Slide | Instructions |
| --- | --- |
| Intention survey discussion | - Begin the activity with a plenary discussion based on the following questions: - Why is intention survey information relevant to CM? - What type of information is included in a CM survey? - Is it the responsibility of the CM team to conduct such surveys? - What is your experience with intention surveys? - Ask the group to brainstorm what type of information they would like to include on a returns survey for their setting. - Use Annex 12.5 as an example if needed. |
| Key message | ## Recap on key message: Intention surveys provide a good overview of IDPs’ future plans and preferred choices in relation to long-term solutions, including their perceptions about the general situation back home, existing issues and concerns related to their life in displacement and the main aspects preventing them from leaving the site. Facilitator’s tip: Ask the participants to discuss the key message before changing slide from photo to message. |

6. Site closure process

Activity 6A: Developing an action plan for closure

Learning objective

Plan the key aspects of site closure.

Preparation and materials

- Flipchart paper for each group to brainstorm

- Print Annex 12.6

Duration:									                 45 min

| Slide | Instructions |
| --- | --- |
| Elements of a local/site closure action plan | - Building on the outcomes of Activity 3, the participants should now focus on the “how” of closing a site according to international standards, exploring the tools and systems to put in place to implement the actions described under each responsibility. |
| Group work | - Organise the plenary in three groups. Group selection can be voluntary. Each group will develop an action plan for a site closure. - Group 1: Population elements relate directly to the displaced population and the host community, both within the camp and areas of return. - Group 2: Infrastructural elements relate to the infrastructure and land, including decommissioning of a camp area. - Group 3: Operational elements relate to the movements, logistics, information and security throughout the closure process - Remind participants that GBV mainstreaming is critical in the closure workplan. - Debrief by group, using Annex 12.6 to make sure that all considerations are identified. |
| Key messages | ## Recap on key messages: States have the primary duty to establish conditions which allow displaced persons to benefit from durable solutions voluntarily, and in safety, security and dignity. Site closure action plans are built based on a National Exit Strategy that provides the overall approach, context and principles for phasing out camp-based assistance. Local/site closure action plans shall elaborate on: people elements, infrastructure aspects and also support/operational activities. Facilitator’s tip: Ask the participants to discuss the key message before changing slide from photo to message. |
| Questions | Address any questions or comments |
| END OF MODULE |  |

Activity 6B: Role play on presenting an action plan

Learning objective

Plan the key aspects of site closure.

Preparation and materials

- Set up the room for the role play, which is based on a meeting

Duration:									                 60 min

| Slide | Instructions |
| --- | --- |
| Group work | - Meaningfully divide the plenary into three groups depending on their profiles. - Assign two groups to be the camp managers. They will have separate tasks: one will be responsible for the “population elements” while the other will be responsible for the “infrastructure of the camp site.” - Assign the 3rd group to be coordinators. Their objective in the role play is to ensure consistency across sites with a focus on standards and compliance with the national exit plan as presented in Activity 3. - Groups will have to work together to organise a presentation for the national authorities (the trainers) outlining their action plan. - Allow 20 minutes for the groups to prepare their presentations. In your role as the national authorities, call the meeting to order and begin the role play, putting everyone into character. Allow the role play to progress for 30 minutes. |
| Key message | ## Recap on key message: States have the primary duty to establish conditions which allow displaced persons to benefit from durable solutions voluntarily, and in safety, security and dignity. Site closure action plans are built based on a National Exit Strategy that provides the overall approach, context and principles for phasing out camp-based assistance. Local/site closure action plans shall elaborate on: people elements, infrastructure aspects and also support/operational activities. Facilitator’s tip: Ask the participants to discuss the key message before changing slide from photo to message. |
| Questions | Address any questions or comments |
| END OF MODULE |  |

IASC. 2015. Guidelines for Integrating Gender-Based Violence Interventions in Humanitarian Action: Reducing risk, promoting resilience and aiding recovery. Page 61. https://gbvguidelines.org/en/home/