**Shelter Cluster Nepal Timeline**

|  |  |  |
| --- | --- | --- |
| **Start Date** | **End Date** | **Key Personnel** |
| 25 April 2015 | 31 January 2016 | Pablo Medina - Deputy Global Cluster Coordinator (remote support) |
| 25 April 2015 | 31 January 2016 | Sanjeev Hada - National Coordinator |
| 27 April 2015 | 24 May 2015 | Victoria Stodart - National Coordinator |
| 27 April 2015 | 20 May 2015 | Neil Bauman - Global Focal Point (Coordination/IM) |
| 29 April 2015 | 11 May 2015 | Joseph Ashmore - Global Focal Point (Technical) |
| 21 May 2015 | 03 September 2015 | Victoria Bannon - National Coordinator |
| 24 July 2015 | 31-Dec-15 | Tom Bamforth Global Focal Point (Coordination) |
| 1 November 2015 | 22 November 2015 | Wardell Eastwood – Regional Focal Point |
| 28 November 2015 | 7 December 2015 | Neil Bauman - Global Focal Point (Coordination/IM) |
| 7 December 2015 | 14 December 2015 | Wardell Eastwood – Regional Focal Point |

|  |  |
| --- | --- |
| **Start Date** | **Key Events and Decisions** |
| 28 April 2015 | First Shelter Cluster Meeting |
| 29 April 2015 | First Shelter Cluster Technical Meeting |
| 09 May 2015 | HC Decision on 3 Hubs |
| 21 May 2015 | Shelter Cluster Accountability TWG |
| 25 May 2015 | Key Messages Shelter TWG |
| 27 May 2015 | Shelter Intervention TWG |
| 31 May 2015 | Capacity Building and Training Shelter TWG |
| 02 June 2015 | Cash, Markets & Livelihoods & Shelter Specification TWG |
| 08 June 2015 | Technical Assistance and Training TWG |
| 09 June 2015 | Capacity Building TWG |
| 09 June 2015 | Cash & Shelter TWG |
| 30 July 2015 | Winterization TWG |
| 04 August 2015 | Recovery & Reconstruction WG |

|  |  |
| --- | --- |
| **Date** | **Key Deliverables** |
| 29 April 2015 | Flash Appeal |
| 29 April 2015 | Weekly 3W/4W data collection & related IM products (continuous) |
| 29 April 2015 | Draft Shelter Cluster Strategy |
| 02 May 2015 | Technical Reference Library compiled |
| 06 May 2015 | First IM product on tarpaulin distribution |
| 08 May 2015 | First Technical IEC Guidelines (Nepali) |
| 16 May 2015 | Finalised SC Strategy (first draft) |
| 21 May 2015 | Finalised Technical Modalities Guidelines (first draft) |
| 27 May 2015 | Revised Flash Appeal |
| 15 July 2015 | IEC Safe Location & Preparedness |
| 07 August 2015 | Technical Specifications published |
| 08 September 2015 | Post Distribution Monitoring |
| 24 September 2015 | Winterization Guidance |
| 09 October 2015 | IEC Materials for Safe Demolition and Material Reuse |
| 13 October 2015 | Recovery & Reconstruction WG 6 Month Workplan |
| 04 November 2015 | 10 Key Messages for Building Back Safer |
| 20 November 2015 | Winterization Guidance & Recommended Package |